## Checklist
SOP-Link in grey | Tasks |  | Command | unit_1104 |  | hide columns |  | hide columns |  | hide columns |  | hide columns |  | Date | Comments | Extra | Extra | Extra | Extra
SLC-CL-DEP05 Slocum deployment checklist
Deployment mission:
Current Engineer:
Date Deployed:
Deployment
Fill in below
number of gliders: | 1
| Glider names | Is there a MR installed
Glider Name 1: | unit_1104 | no
| na | na
| na | na
| na | na
| na | na
SOP-Link in grey | Section name | tasks | Command | task complete | section complete | task complete | section complete | task complete | section complete | task complete | section complete | task complete | section complete | Date | Comments | Extra | Extra | Extra | Extra
Deployment |  |  |  | Task Complete | Section Incomplete | Task Complete | Section Complete | Task Complete | Section Complete | Task Complete | Section Complete | Task Complete | Section Complete | Date | Comments
Pre-Deployment |  |  |  | Incomplete |  | Complete |  | Complete |  | Complete |  | Complete
| SFMC Admin archive Deployment on SFMC |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| Cache files |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| test remote comms |  | Cell - iridium go - iridium handset etc | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| remote team confirms local testing done (not done) |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| remote team relays glider turn over plan and ETA |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| Run a simulation (optional). Check all files and data. |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| Download all relevant glider/sensors files and build the final version of the Expedition folder. Send it to the office/SharePoint if possible. |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  | *.ma, *.mi, config files (science and flight), Microrider SETUP.CFG, etc | - | - | - | -
|  |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
on deck |  |  |  | Incomplete |  | Complete |  | Complete |  | Complete |  | Complete
| Note time |  | ensure remote teams has unplugged freewave | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| stop initial.mi |  | Ctrl-C x 2 | y |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| increase time in gliderdos |  | put u_max_time_in_gliderdos 3600 | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| optionally pull all config files eng or autoexec.mi and sbdlist.dat |  | zs config/autoexec.mi zs config/sbdlist.dat | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| optionally pull all config files sci or proglets.dat and tbdlist.dat |  | szs /config/proglets.dat szs config/tbdlist.dat | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| ensure vanila mission and mafiles pres |  | (optionally type or send off or on) | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| send in new goto and any new files |  | dockzr *.* | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| status.mi |  | run status.mi | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| confirm status.mi completes normally, there should be no aborts OR any aborts that have been sorted and understood |  | why? | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| confirm location#send sbd tbd, look at age of fix |  | where | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| plot eng and sci data |  | send *.sbd *.tbd | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| confirm eng data in datavisualizer |  | You may need to provide cache file from Lab SFMC or send off glider | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| confirm sci data in datavisualizer |  | battery-vacuum-time-gps position-leak detects | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| confirm devices do not have unusually high number of warnings or oddities |  | use | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| communicate to remote team if glider is okay to deploy |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  | From now on, the pilot team is responsible for control of the glider | - | - | - | -
|  |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
In Water |  |  |  | Incomplete |  | Complete |  | Complete |  | Complete |  | Complete
| remote team has communicated glider is deployed and is on or off bouy |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| status.mi |  | run status.mi | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| confirm surface dialog enf data |  | battery-vacuum-time-gps position-leak detects | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| confirm no aborts |  | why? | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| zero ocean pressure |  | zero_ocean_pressure | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| run ini0.mi (on bouy prefered) |  | run ini0.mi | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| send mdb |  | send *.mbd -num=1 | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| send all sbd and tbd (should be ini0 and status only) |  | send *.sbd *.tbd | N |  | NA |  | NA |  | NA |  | NA
| exit reset and catch glider on connection |  | exit reset | N |  | NA |  | NA |  | NA |  | NA
| confirm ballast |  | Is dive climb shaped like a nice V - if not use drive calculator ---> | N |  | NA |  | NA |  | NA |  | NA
glider drive calculator | if not V inform crew of how many weights to add or remove and repeat ini0 |  |  | N |  | NA |  | NA |  | NA |  | NA
| if ballast OK - Notify crew to remove bouy |  |  | N |  | NA |  | NA |  | NA |  | NA
| once notified glider is free - sequence mission.mi(5) |  | Sequence mission.mi(5) --- often an expedition specific mission name will substitute | N |  | NA |  | NA |  | NA |  | NA
| first vanila mission dive is 30 m |  |  | N |  | NA |  | NA |  | NA |  | NA
| confirm script is running |  | Select or play script SFMC-g3s-ma-first-num=3.xml | N |  | NA |  | NA |  | NA |  | NA
| after this adjust dive depth and altitude per operations |  | depth increases are typically 100 300 600 990 (edit yo35.ma) | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| adjust autoballast values as appropriate |  | look at max and min pumped in the header c_dive_bpump | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| in mission during surface dialog optionally turn off or on current correction |  | !put u_use_current_correction 0 | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| notify field crew that glider is on mission diving to full depth |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
|  |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
|  |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
|  |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
Remainder of day 1 (or in day 2) |  |  |  | Incomplete |  | Complete |  | Complete |  | Complete |  | Complete
| possilby increase number of half yos |  | Increase no comms and number of yo as | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| increase no comms |  | navigation, data retrieval and nominal operation is confirmed | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| adjust density of eng data as desired (sbdlist.dat) |  | edit sbdlist.dat (restart mission) | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| adjust density of sci data as desired (tbdlist.dat) |  | edit tbdlist.dat (put in to-science) | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| compare actual result to campaign plan and verify with lead pilot all requirements are being met or will be |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| subscribe to aborts sms and/or calls |  | GliderLab | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| set SFMC email subscriptions |  | glider specific page then options>Configure Glider Event Subscriptions | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| adjust min depth for alt - example here turn altimeter on the 40m and deeper |  | !put u_alt_min_depth 40 | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
|  |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
|  |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
|  |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
Day 2 and beyond |  |  |  | Incomplete |  | Complete |  | Complete |  | Complete |  | Complete
| daily logs and paste to C2 |  | SLC-CL-PLT05 Pilot log checklist.xlsx | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
| ensure deployment specific criteria are being satisfied - energy budget - science requirements - navigation requirements |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
|  |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
|  |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -
|  |  |  | N |  | NA |  | NA |  | NA |  | NA |  |  |  | - | - | - | -

## NOTES (hidden)
NOTES
This Top section can be pulled by code with Sensor Tracker, Would need to test this
Idea I have is you start your prep on gliderlab webpage and download a zip file with all the basic stuff input for you. In a hidden sheet baserd off the glider you are working on
Cells D3:D18 get completed for you as you fill in the sheet
Cells G3:G8(adding more for specific sensors this is just an example) again get added based off sensor tracker
Meta data will be inputs of SN. Should not be nessisary just thought maybe….
You fill in y or n for the task complete row in the form below
the section done will bne auto filled based off formula
Macro (steve, I do not understand excel macros, I hate excel for stuff like that, so someone else could take that on) once Section task is complete, it gets hidden after you press update button or whatever
This is just an example, based of the preliminary list Ben gave. We would have to add more details as we go.
Specific sections could warent an SOP. Some may not need one. Sections for comments if needed for individual tasks. Like if you changed your pump mid way, add that in as a comment

## Change Log
Version | Contributor | Change Log
1 | Ben | initial
1.1 | AC | changed over to use CL format
1.2 | AC | Fixed formating
1.1.1 | FS | added MR stuff